## Slide 1
Sportsbook Programme
World Cup MVP Delivery Plan | March 2026
16 Work Packages | 4 Deliverables | 8 Domain Teams
Soft Launch: Apr 1 | Go-Live: May 1 | World Cup: Mid-June 2026
Scope: Soccer only | Pre-match | USD | en-US | Web (desktop + mobile) | 4 brands

## Slide 2
4 Deliverables — Each a Demoable Increment
1. Central Offering Foundation
Punter opens the sportsbook and browses World Cup fixtures with live odds
6 WPs: FEEDS, OFFER, FRONTEND, BETTING, DATA
2. Betslip Core & Placement Flow
Punter builds a bet, places it, gets validated. Operator controls limits and kill switch
11 WPs: FRONTEND, BETTING, OFFER, DATA
3. My Bets & Real Data Connection
Bets settle from real results. Real money moves. Punter sees bet history live
10 WPs: BETTING, DATA, FRONTEND, FEEDS, OFFER
4. Operation Control & Visibility
Traders manage the book via Kraken. Splunk dashboards show full operational picture
14 WPs: BACKOFFICE, BETTING, DATA, SPLUNK

## Slide 3
16 Work Packages
1 Simple Parlay — Combine bets from different matches
2 Soccer WC Hub — World Cup landing page with fixtures & markets
3 Settlement — Auto-grade and settle bets from real results
4 Book On/Off Switch — Emergency kill switch + punter blocking
5 Bet Placement Controls — Stake limits, payout caps, odds validation
6 Central Offer Foundation — Own our offer data, not the feed provider's
7 Bet Ticker — Live bet feed for traders
8 RT Liability — Real-time book exposure by market
9 Manual Resettlement — Traders correct grading errors and void bets
10 Audit Trail — Who changed what, when, why
11 RT Odds Display — Live odds updates + suspended market indicators
12 My Bets — Punter checks active and settled bets
13 Bet History — Traders investigate punter betting activity
14 SGP — Same-game parlay with correlated pricing
15 Mega Parlay — SGPs + straights across matches
16 Feed Health — Detect unhealthy feeds, protect from stale data

## Slide 4
Work Package Status — Live from Jira (25 Mar 2026)
1 COMPLETED: Straight Bet (SA-15) — Post-Delivery Assessment
11 IN DELIVERY:
SA-66 Central Offer | SA-14 WC Hub | SA-17 Simple Parlay | SA-22 Settlement
SA-20 Bet Controls | SA-25 Bet Ticker | SA-24 RT Liability | SA-26 Bet History
SA-27 My Bets | SA-71 Feed Health | SA-28 Audit Trail
4 READY FOR HANDOVER:
SA-19 RT Odds Display | SA-21 Book On/Off | SA-23 Manual Resettlement | SA-28 Audit Trail
2 SCOPE VALIDATION (blocked):
SA-16 SGP | SA-18 Mega Parlay

## Slide 5
Deliverable 1: Central Offering Foundation
FEEDS — WP 2,6,11,16 — WC data flows from OpticOdds. No feed = no sportsbook
OFFER — WP 2,6,11,16 — We own our offer, not a pass-through of OpticOdds
FRONTEND — WP 2,6,11,16 — WC Hub page, navigation, real-time odds, suspended markets
BETTING — WP 11,16 — SGP prices refresh on odds change. Stop bets when feed is down
DATA — WP 2,6,11,16 — Odds history in Splunk. Diffusion for real-time frontend
SPLUNK RAW — WP 2,6,16 — Offer events, odds history, feed health dashboard

## Slide 6
Deliverable 2: Betslip Core & Placement Flow
FRONTEND — WP 1,4,5,14,15 — Combined odds, winnings, errors. Kill switch darkens site. SGP feedback
BETTING — WP 1,4,5,7,8,13,14,15,16 — Core upgrade: parlay+SGP+Mega. Limits. Kill switch. Real wallet
OFFER — WP 4,5,14,15 — Business defines rules: limits, bet types, SGP/Mega config
DATA — WP 1,4,5,7,8,13,14,15,16 — Every bet in reports. Ticker+Liability start. Rejected bets
SPLUNK RAW — WP 1,16 — First multi-leg bet events. Feed health monitoring

## Slide 7
Deliverable 3: My Bets & Real Data Connection
FRONTEND — WP 3,12 — Punter sees Pending>Won/Lost. My Bets = core punter experience
BETTING — WP 3,7,8,9,12,13,14,15 — Where the business makes/loses money. Real grading+wallet
FEEDS — WP 3 — Match results from OpticOdds. Without results, no bets settle
OFFER — WP 3 — Results through our offer resolution. We own the grading
DATA — WP 3,7,8,9,12,13 — Settlement feeds P&L. Liability updates. Manual audit. My Bets push
SPLUNK RAW — WP 3,12 — Every grading decision, wallet transaction, resettlement

## Slide 8
Deliverable 4: Operation Control & Visibility
BACKOFFICE — WP 4,5,9,10 — Kraken: kill switch, limits, manual settle, audit trail
BETTING — WP 4,5,7,9,10,13 — Kill switch blocks API. Limits enforced. Manual settle engine. Audit
OFFER — WP 4,5 — Operator Management: master switch and limit config
DATA — WP 4,5,7,8,9,10,11,13,16 — All dashboards: Ticker, Liability, Audit, Odds, Feed Health
SPLUNK BUSINESS — WP 4-11,13-16 — Trader's operational cockpit for game day

## Slide 9
Domain Team Workload
WP assignments per team across all 4 deliverables:
Feeds: D1=4 D2=1 D3=1 D4=1 Total=7
Offer: D1=4 D2=4 D3=1 D4=2 Total=11
Frontend: D1=4 D2=5 D3=2 D4=— Total=11
Betting: D1=2 D2=9 D3=8 D4=6 Total=25 *** HEAVIEST
Data: D1=4 D2=9 D3=6 D4=9 Total=28 *** HEAVIEST
BackOffice: D1=— D2=— D3=— D4=4 Total=4
Splunk: D1=3 D2=2 D3=2 D4=12 Total=19
Betting and Data carry the heaviest load across the programme.

## Slide 10
Dependencies & Risks
CRITICAL PATH:
WP 6 Central Offer > WP 2, 11, and all downstream (Foundation)
WES Wallet > WP 1, 3, 5, 9 (Blocks 4 WPs — real money can't move)
PAM Auth > WP 1, 5 (Blocks 2 WPs)
WP 1 Simple Parlay > WP 14 SGP > WP 15 Mega Parlay (Sequential)
TOP RISKS:
[HIGH] Mega Parlay & SGP still in Scope Validation — cannot estimate or plan
[HIGH] Shared DB schema refactor (SBK-2008) — blocks Simple Parlay + Settlement
[HIGH] WES Wallet integration timeline — cascades across 4 WPs
[MED] Splunk vs New Relic strategy undefined — affects all reporting WPs
[MED] Feed Health > Betting suspension unscoped — no WP owns this end-to-end

## Slide 11
Scope: In vs Out (v1.55)
IN SCOPE (MUST HAVE):
Pre-match betting on World Cup fixtures
Straight, Simple Parlay, SGP, Mega Parlay
Real settlement from OpticOdds results
Operator controls (kill switch, limits, manual settle)
Bet Ticker, Liability, Audit Trail in Splunk
Web desktop + mobile responsive | 4 brands | USD | en-US
5,000 bets/min | 500ms odds latency | 99.9% uptime
SHOULD HAVE: In-Play betting | Futures (straights only) | Fractional odds
OUT OF SCOPE (v1.7+): Multi-currency | Multi-language | Cash Out | Native apps
Custom markets | Dynamic margins | Per-punter value factors | Other sports
REDUCED FOR v1.55: Traders Hub UI = API only | BackOffice limits absorbed into Betting

## Slide 12
Planning Framework — 4 Zoom Levels
ZOOM 01 — Business Value Mapping [DONE]
Gate: Product + WPs defined
What to demo, what work per domain. Output: 4 Deliverables, 16 WPs, business WHY
ZOOM 02 — Order & Estimates [NEXT]
Gate: After Architecture Handover
Sequence per domain, T-shirt estimates (weeks), cross-domain dependencies
ZOOM 03 — Milestones & Demo Dates [PENDING]
Gate: After Software Design
Concrete dates per deliverable demo, man-day estimates per feature
ZOOM 04 — Sprint-Level JIRA Plan [PENDING]
Gate: After Team Refinement
Story points per sprint, detailed assignments, velocity-based forecasting

## Slide 13
SDLC Funnel — How Work Packages Progress
Product > Architecture > SOFTWARE DESIGN (UNLOCK) > Team Refine > Execution
Owners per stage:
Product: Kurt / Stakeholders
Architecture: Matus / Solutions
Software Design: Team Principal <<<< UNLOCK POINT
Team Refine: Team Refine (estimates)
Execution: AWS Stage > PPD > Production (full delivery pipeline)
After Software Design, work fans out into parallel streams:
Dev Estimates > Sprint > Demo
QA Estimates > Sprint > Demo
DevOps Plan > Sprint > Demo
Data Plan > Sprint > Demo
FE Plan (can start before SD with mocks)
Sprint Review 1 > Sprint Review 2 > Deliverable Demo

## Slide 14
WP Progress Through the Funnel
Product+Arch done, now in Software Design:
SA-66 Central Offer | SA-14 WC Hub | SA-17 Simple Parlay
SA-22 Settlement | SA-20 Bet Controls | SA-25 Bet Ticker
SA-24 RT Liability | SA-27 My Bets | SA-71 Feed Health
Architecture complete, waiting for delivery pickup:
SA-19 RT Odds Display | SA-21 Book On/Off
SA-23 Manual Resettlement | SA-28 Audit Trail
Still in Scope Validation (BLOCKED):
SA-16 SGP | SA-18 Mega Parlay
Execution = AWS Stage > PPD Done > Production
Full delivery tracked across 3 environments
Key: 9 WPs in Software Design. SD completion unlocks parallel estimation.
The SD column is the bottleneck we track weekly.

## Slide 15
Epic Progress — Child Tickets (SBK-669)
Epic Team Tickets Done%
─────────────────────────────────────────────────────────────────
[FE] Straight Bet (SBK-1951) Frontend 39 33% (13 done / 13 prog / 13 todo)
[BE] Simple Parlay (SBK-2199) Betting Engine 34 32% (11 done / 15 prog / 8 todo)
[BE] Central Offer (SBK-3006) Offer Mgmt 17 6% (1 done / 8 prog / 8 todo)
[WC] Market Parser (SBK-1897) Feeds Mgmt 11 45% (5 done / 1 prog / 5 todo)
[BE] Feed Health (SBK-3094) Feeds Integ 10 0% (0 done / 4 prog / 6 todo)
[BE] Settlement (SBK-2200) Delivery 9 0% (0 done / 3 prog / 6 todo)
Soccer WC Hub (SBK-2189) Delivery 9 0% (0 done / 0 prog / 9 todo)
Bet Ticker/History (DATA-22) Data 1 0% (0 done / 1 prog / 0 todo)
Resulting PreGame (SBK-3516) Feeds Mgmt 1 0% (0 done / 0 prog / 1 todo)
[QA] Straight Bet (SBK-3790) BE QAs 1 0% (0 done / 1 prog / 0 todo)
TOTALS: 132 tickets | 30 Done (23%) | 48 In Progress | 54 To Do

## Slide 16
Where We Are & Next Steps
CURRENT POSITION: Zoom Level 01 DONE | Zoom Level 02 STARTING
WP PIPELINE: 1 Done | 11 In Delivery | 4 Ready for Handover | 2 Scope Validation
IMMEDIATE ACTIONS:
1. Unblock SGP & Mega Parlay
Architecture to complete scope validation for SA-16 and SA-18
2. Start Zoom Level 02 for 15 WPs
DMs fill in delivery order, T-shirt estimates, dependencies
3. Platform Decision: Splunk vs New Relic
Affects 8+ reporting/audit WPs. Decision needed before Z02 estimates for Data
4. Confirm External Timelines
WES Wallet (blocks 4 WPs) and PAM Auth (blocks 2 WPs)
5. Pick Up 4 Handover WPs
RT Odds, Book On/Off, Manual Resettlement, Audit Trail — waiting for capacity